## easyGantt
title | Atlas Sprint Schedule | sprint | name | complete | start | end | puml | puml | @startgantt | @startgantt | Ideate
|  | phase | Ideate | 100% | 2024-11-19 | 2024-12-19 | [Ideate] starts on 2024-11-19 and ends on 2024-12-19 | [Ideate] is 100% completed | <style> |  | Proof of Concept
header |  | phase | Proof of Concept | 100% | 2024-12-20 | 2025-03-19 | [Proof of Concept] starts on 2024-12-20 and ends on 2025-03-19 | [Proof of Concept] is 100% completed | ganttDiagram { | <style> | Prototype
footer | generated: %date("YYYY-MM-dd") |  | Architect | 100% | 2024-12-20 | 2025-01-03 | [Architect] starts on 2024-12-20 and ends on 2025-01-03 | [Architect] is 100% completed | task { | ganttDiagram { | Restricted Preview
caption |  |  | Design | 100% | 2025-01-04 | 2025-01-18 | [Design] starts on 2025-01-04 and ends on 2025-01-18 | [Design] is 100% completed | BackGroundColor #ffe6e6 | task { | Invite Preview
|  |  | Backend | 100% | 2025-01-19 | 2025-02-02 | [Backend] starts on 2025-01-19 and ends on 2025-02-02 | [Backend] is 100% completed | LineColor White | BackGroundColor #ffe6e6
|  |  | Frontend | 100% | 2025-02-03 | 2025-02-17 | [Frontend] starts on 2025-02-03 and ends on 2025-02-17 | [Frontend] is 100% completed | } | LineColor White
|  |  | Integrate | 100% | 2025-02-18 | 2025-03-04 | [Integrate] starts on 2025-02-18 and ends on 2025-03-04 | [Integrate] is 100% completed | undone { | }
Modify Start/End |  |  | Onboarding | 100% | 2025-03-05 | 2025-03-19 | [Onboarding] starts on 2025-03-05 and ends on 2025-03-19 | [Onboarding] is 100% completed | BackGroundColor LightGray | undone {
| 2024-11-18 | phase | Prototype | 15.94% | 2025-03-20 | 2025-08-05 | [Prototype] starts on 2025-03-20 and ends on 2025-08-05 | [Prototype] is 15.9420289855072% completed | } | BackGroundColor LightGray
| 2026-02-18 |  | Admin & Invites | 100% | 2025-03-20 | 2025-04-09 | [Admin & Invites] starts on 2025-03-20 and ends on 2025-04-09 | [Admin & Invites] is 100% completed | } | }
|  |  | Renderer R&D | 15.38% | 2025-04-09 | 2025-04-22 | [Renderer R&D] starts on 2025-04-09 and ends on 2025-04-22 | [Renderer R&D] is 15.3846153846154% completed | </style> | }
back | #ffe6e6 |  | Quill Enhancements - pictures, tables | 0% | 2025-04-23 | 2025-05-07 | [Quill Enhancements - pictures, tables] starts on 2025-04-23 and ends on 2025-05-07 | [Quill Enhancements - pictures, tables] is 0% completed | title Atlas Sprint Schedule | </style>
undone | LightGray |  | Markdown | 0% | 2025-05-08 | 2025-05-22 | [Markdown] starts on 2025-05-08 and ends on 2025-05-22 | [Markdown] is 0% completed | projectscale monthly zoom 3
|  |  | PlantUML & Latex | 0% | 2025-05-23 | 2025-06-06 | [PlantUML & Latex] starts on 2025-05-23 and ends on 2025-06-06 | [PlantUML & Latex] is 0% completed | hide footbox | title Atlas Sprint Schedule
|  |  | Content Safety API | 0% | 2025-06-07 | 2025-06-21 | [Content Safety API] starts on 2025-06-07 and ends on 2025-06-21 | [Content Safety API] is 0% completed | footer generated: %date("YYYY-MM-dd") | projectscale monthly zoom 3
|  |  | Structure Sharing | 0% | 2025-06-22 | 2025-07-06 | [Structure Sharing] starts on 2025-06-22 and ends on 2025-07-06 | [Structure Sharing] is 0% completed | Project starts 2024-11-18 | hide footbox
|  |  | Cross-Structure Reporting | 0% | 2025-07-07 | 2025-07-21 | [Cross-Structure Reporting] starts on 2025-07-07 and ends on 2025-07-21 | [Cross-Structure Reporting] is 0% completed | [Ideate] starts on 2024-11-19 and ends on 2024-12-19
|  |  | User Metrics | 0% | 2025-07-22 | 2025-08-05 | [User Metrics] starts on 2025-07-22 and ends on 2025-08-05 | [User Metrics] is 0% completed | [Proof of Concept] starts on 2024-12-20 and ends on 2025-03-19
|  | phase | Restricted Preview | 0% | 2025-08-06 | 2025-12-03 | [Restricted Preview] starts on 2025-08-06 and ends on 2025-12-03 | [Restricted Preview] is 0% completed | [Architect] starts on 2024-12-20 and ends on 2025-01-03 | footer generated: %date("YYYY-MM-dd")
|  |  | Platform Metrics & Alerting | 0% | 2025-08-06 | 2025-08-20 | [Platform Metrics & Alerting] starts on 2025-08-06 and ends on 2025-08-20 | [Platform Metrics & Alerting] is 0% completed | [Design] starts on 2025-01-04 and ends on 2025-01-18
|  |  | Test Automation | 0% | 2025-08-21 | 2025-09-04 | [Test Automation ] starts on 2025-08-21 and ends on 2025-09-04 | [Test Automation ] is 0% completed | [Backend] starts on 2025-01-19 and ends on 2025-02-02
|  |  | Web Analytics | 0% | 2025-09-05 | 2025-09-19 | [Web Analytics] starts on 2025-09-05 and ends on 2025-09-19 | [Web Analytics] is 0% completed | [Frontend] starts on 2025-02-03 and ends on 2025-02-17 | Project starts 2024-11-18
|  |  | LLM Ingest | 0% | 2025-09-20 | 2025-10-04 | [LLM Ingest] starts on 2025-09-20 and ends on 2025-10-04 | [LLM Ingest] is 0% completed | [Integrate] starts on 2025-02-18 and ends on 2025-03-04
|  |  | Penetration Testing | 0% | 2025-10-05 | 2025-10-19 | [Penetration Testing] starts on 2025-10-05 and ends on 2025-10-19 | [Penetration Testing] is 0% completed | [Onboarding] starts on 2025-03-05 and ends on 2025-03-19
|  |  | Cost Optimization | 0% | 2025-10-20 | 2025-11-03 | [Cost Optimization] starts on 2025-10-20 and ends on 2025-11-03 | [Cost Optimization] is 0% completed | [Prototype] starts on 2025-03-20 and ends on 2025-08-05
|  |  | Automated Scaling | 0% | 2025-11-04 | 2025-11-18 | [Automated Scaling] starts on 2025-11-04 and ends on 2025-11-18 | [Automated Scaling] is 0% completed | [Admin & Invites] starts on 2025-03-20 and ends on 2025-04-09
|  |  | Payment Processing | 0% | 2025-11-19 | 2025-12-03 | [Payment Processing] starts on 2025-11-19 and ends on 2025-12-03 | [Payment Processing] is 0% completed | [Renderer R&D] starts on 2025-04-09 and ends on 2025-04-22
|  | phase | Invite Preview | 0% | 2025-12-04 | 2026-02-16 | [Invite Preview] starts on 2025-12-04 and ends on 2026-02-16 | [Invite Preview] is 0% completed | [Quill Enhancements - pictures, tables] starts on 2025-04-23 and ends on 2025-05-07
|  |  | Design Review | 0% | 2025-12-04 | 2025-12-18 | [Design Review] starts on 2025-12-04 and ends on 2025-12-18 | [Design Review] is 0% completed | [Markdown] starts on 2025-05-08 and ends on 2025-05-22
|  |  | Design Adaptation | 0% | 2025-12-19 | 2026-01-02 | [Design Adaptation] starts on 2025-12-19 and ends on 2026-01-02 | [Design Adaptation] is 0% completed | [PlantUML & Latex] starts on 2025-05-23 and ends on 2025-06-06
|  |  | Regulatory Review | 0% | 2026-01-03 | 2026-01-17 | [Regulatory Review] starts on 2026-01-03 and ends on 2026-01-17 | [Regulatory Review] is 0% completed | [Content Safety API] starts on 2025-06-07 and ends on 2025-06-21
|  |  | User Acq. & Marketing plan | 0% | 2026-01-18 | 2026-02-01 | [User Acq. & Marketing plan] starts on 2026-01-18 and ends on 2026-02-01 | [User Acq. & Marketing plan] is 0% completed | [Structure Sharing] starts on 2025-06-22 and ends on 2025-07-06
|  |  | Business Plan | 0% | 2026-02-02 | 2026-02-16 | [Business Plan] starts on 2026-02-02 and ends on 2026-02-16 | [Business Plan] is 0% completed | [Cross-Structure Reporting] starts on 2025-07-07 and ends on 2025-07-21
|  |  | Launch |  | 2026-02-17 |  | [Launch] happens on 2026-02-17 |  | [User Metrics] starts on 2025-07-22 and ends on 2025-08-05
[Restricted Preview] starts on 2025-08-06 and ends on 2025-12-03
[Platform Metrics & Alerting] starts on 2025-08-06 and ends on 2025-08-20
[Test Automation ] starts on 2025-08-21 and ends on 2025-09-04
[Web Analytics] starts on 2025-09-05 and ends on 2025-09-19
[LLM Ingest] starts on 2025-09-20 and ends on 2025-10-04
[Penetration Testing] starts on 2025-10-05 and ends on 2025-10-19
[Cost Optimization] starts on 2025-10-20 and ends on 2025-11-03
[Automated Scaling] starts on 2025-11-04 and ends on 2025-11-18
[Payment Processing] starts on 2025-11-19 and ends on 2025-12-03
[Invite Preview] starts on 2025-12-04 and ends on 2026-02-16
[Design Review] starts on 2025-12-04 and ends on 2025-12-18
[Design Adaptation] starts on 2025-12-19 and ends on 2026-01-02
[Regulatory Review] starts on 2026-01-03 and ends on 2026-01-17
[User Acq. & Marketing plan] starts on 2026-01-18 and ends on 2026-02-01
[Business Plan] starts on 2026-02-02 and ends on 2026-02-16
[Launch] happens on 2026-02-17
[Ideate] is 100% completed
[Proof of Concept] is 100% completed
[Architect] is 100% completed
[Design] is 100% completed
[Backend] is 100% completed
[Frontend] is 100% completed
[Integrate] is 100% completed
[Onboarding] is 100% completed
[Prototype] is 15.9420289855072% completed
[Admin & Invites] is 100% completed
[Renderer R&D] is 15.3846153846154% completed
[Quill Enhancements - pictures, tables] is 0% completed
[Markdown] is 0% completed
[PlantUML & Latex] is 0% completed
[Content Safety API] is 0% completed
[Structure Sharing] is 0% completed
[Cross-Structure Reporting] is 0% completed
[User Metrics] is 0% completed
[Restricted Preview] is 0% completed
[Platform Metrics & Alerting] is 0% completed
[Test Automation ] is 0% completed
[Web Analytics] is 0% completed
[LLM Ingest] is 0% completed
[Penetration Testing] is 0% completed
[Cost Optimization] is 0% completed
[Automated Scaling] is 0% completed
[Payment Processing] is 0% completed
[Invite Preview] is 0% completed
[Design Review] is 0% completed
[Design Adaptation] is 0% completed
[Regulatory Review] is 0% completed
[User Acq. & Marketing plan] is 0% completed
[Business Plan] is 0% completed
@endgantt